| UNITED NATIONS |  |  |
| --- | --- | --- |

|  | UNEP/MC/COP.6/INF/25 |
| --- | --- |

|  |  | Distr.: General 07 July 2025 English only |
| --- | --- | --- |

| Conference of the Parties to the Minamata Convention on Mercury Sixth meeting Geneva, 3–7 November 2025 Item (j) (ii) of the provisional agenda* Matters for consideration or action by the Conference of the Parties: cross-cutting matters: implementation of decision MC-5/15 |  |
| --- | --- |

Status of implementation of decision MC-5/15 during the 2024–2025 biennium**

Note by the secretariat

- As is mentioned in the note by the secretariat on “Activities to address health concerns of women and children in the 2026–2027 biennium” (UNEP/MC/COP.6/18), the annex to the present note sets out a review of activities undertaken by the secretariat and parties during the 2024–2025 biennium pursuant to decision MC-5/15. The list of activities to implement the gender action plan during the 2024–2025 biennium, as identified by the Conference of the Parties at its fifth meeting, is set out in paragraphs 1 and 2 of annex I to document UNEP/MC/COP.5/18.

Annex

Review of activities to implement decision MC-5/15 during the 2024–2025 biennium

| Activities | Indicators of achievement | Means of verification | Funding source | Responsible actors | Review of activities undertaken |
| --- | --- | --- | --- | --- | --- |
| I. Activities to be carried out by the secretariat |  |  |  |  |  |
| a) Review of national reports submitted by parties under article 21 to identify measures related to the control of mercury-added products used primarily by women and children, such as cosmetics and dental amalgam | Statistics are compiled and review is produced | Baseline report incorporating a review of national reports | Staff time | Secretariat | Status: ongoing The review of the second short national reports is available on Convention’s website. Next steps: the secretariat will review relevant measures included in the second full national reports, which are due by 31 December 2025. |
| b) Analysis of strategies to prevent exposure of women and children to mercury in existing national action plans submitted by parties pursuant to subparagraph 3 (a) of article 7 to establish a baseline for future reviews of national action plans, in collaboration with the Chemicals and Health Branch of the United Nations Environment Programme (UNEP) | Statistics are compiled and review is produced | Baseline report incorporating a review of national action plans | Funded by Finland | Secretariat, UNEP | Status: ongoing The analysis of national action plans submitted by parties as of June 2025 is available on the Convention’s website. Next steps: the analysis is expected to be integrated in the technical information and tools: review of the implementation of article 7 obligations under the Minamata Convention on Mercury and related training package for parties to be delivered by the Chemicals and Health Branch of the United Nations Environment Programme and the Global Environment Facility. |
| c) Development of case studies of projects addressing health concerns of women and children funded by the Specific International Programme to Support Capacity-Building and Technical Assistance | Statistics are compiled and case studies are produced | Convention’s website | Funded by Finland | Secretariat | Status: done The secretariat has developed four case studies on projects addressing health concerns of women funded by the Specific International Programme. The case studies are available on the Convention’s website. |
| d) Continued inclusion of considerations of women’s empowerment and participation in the process of appraising and evaluating projects under the Specific International Programme | Considerations integrated in the appraising and evaluation process | Application guidelines and guidelines for conducting projects’ terminal reviews and evaluations | Staff time | Secretariat | Status: ongoing The application guidelines for the fourth round of the Specific International Programme included considerations of health concerns of women and children. The guidelines for conducting projects’ terminal reviews and evaluations also include such considerations. More information is available on the Convention’s website. |
| (e) Delivery of training on integrating considerations of women’s empowerment and participation in the development of project proposals in order to access funding under the financial mechanism of the Convention, in collaboration with the GEF secretariat | Webinars delivered | Convention’s website | Staff time | Secretariat | Status: done Following the launch of the fourth round of applications to the Specific International Programme, the secretariat organized webinars for parties presenting information and suggestions from the application guidelines on how to integrate considerations of health concerns of women and children into project proposals. In 2024, the secretariat also organized a Minamata Online session to showcase how such considerations are integrated by the Specific International Programme, the Global Environment Facility and the Special Programme into application criteria for funding, application guidelines, project applications, reporting forms and project evaluation processes. |
| f) Incorporation consideration of of health concerns of women and children into existing training, such as training related to mercury-added products, training for negotiators and potential chairs of contact groups, and training in mercury wastes organized by the secretariat in cooperation with partners, such as the secretariat of the Basel, Rotterdam and Stockholm conventions and GEF | Session on the impacts of mercury exposure on women and children | Presentation and report of the training | Funded by Sweden | Secretariat, BRS secretariat | Status: done A session on the impacts of mercury exposure on women and children was delivered during the BRS training for co-chairs in February 2025. |
| g) Measurement of the meaningful participation of women in meetings of the Conference of the Parties, in Bureau meetings, in other official and expert meetings and in the processes and activities of the secretariat | Statistics are compiled | Nominations and registration of COP-5 participants; election of officers at COP-5; nomination of experts | Staff time | Secretariat | Status: ongoing Information on participation of women is available on Convention’s website. Next steps: the secretariat will continue measuring meaningful participation of women at the sixth and seventh meetings of the Conference of the Parties and other meetings. |
| h) Promotion of efforts to identify “champions” to support the secretariat in its endeavour to address health concerns of women and children into all activities to be undertaken by itself, by parties and by other stakeholders | Establishment of a Women’s Caucus of the Minamata Convention on Mercury | Convention’s website | Staff time | Secretariat | Status: ongoing The secretariat supported the establishment of the Women’s Caucus of the Minamata Convention on Mercury. As of July 2025, more than 70 stakeholders became members of the Women’s Caucus of the Minamata Convention on Mercury. A webinar to identify needs and opportunities for engagement of women was organized in June 2025. More information is available on the Convention’s website. Next steps: the secretariat will support the coordination of the women’s caucus of the Minamata Convention. |
| i) Sharing of parties’ surveys and requests for information to enable the secretariat to identify capacity-building needs and the interests of parties and other stakeholders with respect to mercury exposure of women and children. | Webinar delivered | Convention’s website | Staff time | Secretariat | Status: ongoing On 10 March 2025, the secretariat organized a Minamata Online webinar to provide an overview of the activities undertaken by the secretariat to address health concerns of women and children and invite inputs to proposed priority activities to be carried out during the 2026–2027 biennium. Next steps: the secretariat will continue collecting information from parties and other stakeholders on capacity-building needs and interests with respect to mercury exposure of women and children. |
| II. Activities for parties and other stakeholders |  |  |  |  |  |
| a) Provision of information on health concerns of women and children, as appropriate, in their national reports to be submitted pursuant to article 21 of the Convention | Number of concerns reported by parties | National reports | Staff time | Parties | Status: ongoing The review of the second short national reports is available on Convention’s website. Next steps: the secretariat will review relevant measures included in the second full national reports, which are due by 31 December 2025. |
| b) Integrate and monitor strategies to prevent exposure of women and children to mercury into the review of national action plans to be submitted in accordance with subparagraph 3 (c) of article 7 and subparagraph 1 (i) of annex C to the Convention | Number of strategies reported | National reports | Staff time | Parties, United Nations Environment Programme and the Global Environment Facility. | Status: ongoing The analysis of national action plans submitted by parties as of June 2025 is available on the Convention’s website Next steps: the analysis is expected to be integrated in the technical information and tools: review of the implementation of article 7 obligations under the Minamata Convention on Mercury and related training package for parties to be delivered by the Chemicals and Health Branch of the United Nations Environment Programme and the Global Environment Facility. |
| c) Ensuring that data on the impacts of mercury exposure on women and children is included in the effectiveness evaluation process under article 22, in particular with respect to the monitoring of data on trends in the levels of mercury and mercury compounds observed in biotic media and vulnerable populations, in accordance with paragraph 2 of article 22 | Data included in the reports to the Open-Ended Scientific Group | Reports of the Open-Ended Scientific Group | Staff time | Parties | Status: ongoing The Open-Ended Scientific Group reviewed data on the levels of mercury in vulnerable populations, disaggregated by gender, at its second meeting from 17 to 21 March 2025. More information is available on Convention’s website. |
| d) Responding to surveys and requests for information to enable the secretariat to identify capacity-building needs and interests with respect to mercury exposure of women and children of parties and other stakeholders | Participation in webinar | Convention’s website | Staff time | Parties and other stakeholders | Status: ongoing On 10 March 2025, the secretariat organized a Minamata Online webinar to provide an overview of the activities undertaken by the secretariat to address health concerns of women and children and invite inputs to proposed priority activities to be carried out during the 2026–2027 biennium. |
| e) Inclusion of considerations of women’s empowerment and participation in the terms of reference for the next review of the financial mechanism | Incorporation of performance criterion on women | Draft terms of reference for the third review of the financial mechanism | Staff time | Parties | Status: ongoing The draft terms of reference for the third review of the financial mechanism include, as a performance criterion to be taken into account in assessing the effectiveness of the financial mechanism, the extent to which the projects funded by the financial mechanism have benefited women and taken into account women’s empowerment and participation. |
| f) Ensuring that there is balance in the representation of men and women in delegations to the meetings of the Conference of the Parties and other Convention-related meetings. | Number of men and women in delegations | Lists of participants | Staff time | Parties | Status: ongoing Information on participation of men and women in delegations is available on Convention’s website. |

* UNEP/MC/COP.6/1/Rev.1.

** This document has not been formally edited.

https://minamataconvention.org/en/topics/women-and-girls

https://minamataconvention.org/en/topics/women-and-girls

https://minamataconvention.org/en/topics/women-and-girls

https://minamataconvention.org/en/implementation/specific-international-programme/fourth-round

https://minamataconvention.org/en/resources/minamata-online-mainstreaming-gender-capacity-building-projects

https://minamataconvention.org/en/topics/women-and-girls

https://women4biodiversity.org/womens-caucus-for-the-minamata-convention-on-mercury/

https://minamataconvention.org/en/news/become-member-womens-caucus-minamata-convention-mercury

https://minamataconvention.org/en/resources/implementing-gender-action-plan-minamata-convention

https://minamataconvention.org/en/topics/women-and-girls

https://minamataconvention.org/en/topics/women-and-girls

https://minamataconvention.org/en/intersessional-work-and-submissions-cop-6

https://minamataconvention.org/en/resources/implementing-gender-action-plan-minamata-convention

https://minamataconvention.org/en/topics/women-and-girls